## Sheet1
Requirement No. | Name | Category | Source | Status
Req001 | Tracking for employee Data Software | Software | Project charter | Developing application for the Tracking of the Employee
Req002 | Laptop For Employee | Hardware | Project charter | Complete. Laptops ordered meet requirement by having 16 GB of memory.
Req003 | Incentives | Financial | Project charter | Discussion on Incentives that will motivate employees
Req004 | Not to Cross budget of $200,000 | Financial | Project charter | In Budget
Req005 | Schedule goal is six months | Schedule | Project charter | Currently On time

## Sheet3
Project Description
Manage Your Health, Inc. (MYH) is a Fortune 500 company that provides a variety of healthcare services across the globe. Recently MYH updated its strategic plan, and key goals which include reducing internal costs.The budget for the project is $200,000. An additional $150,000 per year will be required for operational expenses after the project has been completed.Also for next three years and cost about $800,000 each year for development and maintenance.

## Sheet2
Project management-related deliverables:
Business case, charter, team contract, scope statement, WBS, schedule, cost baseline, status reports, final project report, lessons-learned report.

## Sheet4
Product-related deliverables:
Survey current employees for the requirement recreational programs
Database: In order to track employee data on involvement for analysis.
Incentives: Determine incentives that will motivate employees to join and complete programs.
Testing: Testing of the application and make sure it is user friendly.
Promotion: To motivate employees and to announce the benefits for the employees who joins the recreational activity.

## Sheet5
Tasks | Start Date | End Date | Duration
1.0 Initiating | 2017-02-14 | 2017-02-18 | 4
1.1 Identification of Key Stake holders | 2017-02-14 | 2017-02-14 | 1 | 2017-02-14 | 2017-08-14
1.2 Prepare Project Charter | 2017-02-15 | 2017-02-16 | 3
1.3 Initiate Project Meeting with Stake Holders and Responsible Persons | 2017-02-17 | 2017-02-17 | 4
MILE STONE | 2017-02-18 | 2017-02-18
2.0 Planning | 2017-02-19 | 2017-03-03 | 13
2.1 Responsible Team Planning | 2017-02-19 | 2017-02-20 | 2
2.1.1 Team Contract | 2017-02-19 | 2017-02-19 | 0
2.1.2 Team Concerns and Questions | 2017-02-20 | 2017-02-20 | 0
2.2 Identify Discuss projects | 2017-02-21 | 2017-02-22 | 2
2.3 Prioritize tasks | 2017-02-23 | 2017-02-23 | 1
2.4 Prepare Scope Statement | 2017-02-24 | 2017-02-25 | 2
2.5 Prepare WBS | 2017-02-26 | 2017-02-26 | 1
2.6 Create Draft Grant Chart | 2017-02-28 | 2017-02-28 | 1
2.7 Prepare Schedule and cost baseline | 2017-03-01 | 2017-03-03 | 2
2.7.1 Determine Durations | 2017-03-01 | 2017-03-01 | 0
2.7.2 Determine resources | 2017-03-02 | 2017-03-03 | 0
MILE STONE | 2017-03-04 | 2017-03-04 |  |  |  |  | 24
3.0 Executing | 2017-03-05 | 2017-07-05 | 122
3.1 Collect Requirements | 2017-03-05 | 2017-03-20 | 16
3.1.1 Requirement Question | 2017-03-15 | 2017-03-20 | 0
3.2 Application Design | 2017-03-21 | 2017-04-21 | 32 |  |  | 122
3.3 Application Development | 2017-04-22 | 2017-06-10 | 50
3.4 Application Testing | 2017-06-11 | 2017-06-24 | 14
3.5 Application UAT (User acceptance Testing) | 2017-06-25 | 2017-06-30 | 6
3.6 Application Roll out | 2017-07-01 | 2017-07-01
3.7 Application Training | 2017-07-02 | 2017-07-05 | 4
MILE STONE | 2017-07-06 | 2017-07-06
4.0 Monitoring and Controlling | 2017-02-14 | 2017-07-08 | 144
4.1 Monitoring Report | 2017-07-09 | 2017-07-09 | 0
MILE STONE | 2017-07-10 | 2017-07-10
5.0 Closing | 2017-07-10 | 2017-07-15 | 5
5.1 Lessons learned | 2017-07-10 | 2017-07-11 | 2
5.2 Final Report | 2017-07-12 | 2017-07-13 | 2
5.3 Final Presentation | 2017-07-15 | 2017-07-15 | 1