## Report
[Project Title] | [13 empty] | [Company Name / Logo]
Earned Value Analysis Report
Earned Value Management Template
| Prepared By: | [Manager's Name] | [12 empty] | © 2012-2017 Vertex42 LLC
| Date: | [Report Date]
[42]
| For Period: | Week 7
Summary:
[Use this space to write a brief summary or to record specific observations or notes]
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 |  | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1 | 1. Project Management | 95000 | 15833 | 15833 | 15833 | 15833 | 15833 | 15835 |  | ← Enter or edit values in the light-blue cells.
2 | 2. Requirements definition | 11400 | 11400
3 | 3. Web site design | 0
4 | 3.1 Registration for recreational programs |  |  | 3500 | 3500 | 3500
5 | 3.2 Registration for classes and programs |  |  | 3560 | 3560 | 3560
6 | 3.3 Tracking system | 7800 |  | 2600 | 2600 | 2600
7 | 3.4 Incentive system | 7020 |  | 2340 | 2340 | 2340
8 | 4. Web site development | 0
9 | 4.1 Registration for recreational programs | 12600 |  |  |  | 4200 | 4200 | 4200
10 | 4.2 Registration for classes and programs | 13800 |  |  |  | 4600 | 4600 | 4600
11 | 4.3 Tracking system | 8400 |  |  |  | 2800 | 2800 | 2800
12 | 4.4 Incentive system | 6180 |  |  |  | 2060 | 2060 | 2060
13 | 5. Testing | 9600 | [5 empty] | 9600
14 | 6. Training, rollout, and support | 7020 | [5 empty] | 7020
Insert new rows above this one | [9 empty] | ← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
| Total Budgeted Cost | 178820 | 27233 | 27833 | 27833 | 41493 | 29493 | 46115
|  | Cumulative Planned Value (PV) | 27233 | 55066 | 82899 | 124392 | 153885 | 200000
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | [6 empty] | 90000 | [5 empty] | ← Enter the Actual Costs as calculated from the AC worksheet.
|  | Cumulative Earned Value (EV) | [5 empty] | 0 | 100000 | [5 empty] | ← Enter the Earned Value as calculated from the EV worksheet.
120000
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | [6 empty] | 10000 | - | - | - | - | -
|  | Schedule Variance (SV = EV - PV) | [6 empty] | -20000 | - | - | - | - | -
|  | Cost Performance Index (CPI = EV/AC) | [6 empty] | 1.1111 | - | - | - | - | -
|  | Schedule Performance Index (SPI = EV/PV) | [6 empty] | 0.83333 | - | - | - | - | -
|  | Estimated Cost at Completion (EAC) | [6 empty] | 1800.01 | - | - | - | - | -
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012-2017 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1 | 4.3 Tracking system | 95000 | 15% | 50% | 100% | 100% | 100% | 100% | 100%
2 | 2. Requirements definition | 11400 |  | 25% | 30% | 60% | 75% | 90% | 100%
3 | 3. Web site design | 0 |  |  | 25% | 40% | 50% | 100% | 100%
6 | 3.3 Tracking system | 7800 |  |  |  |  | 25% | 80% | 90%
7 | 3.4 Incentive system | 7020 | [5 empty] | 25% | 75%
8 | 4. Web site development | 0 | [6 empty] | 50%
9 | 4.1 Registration for recreational programs | 12600
10 | 4.2 Registration for classes and programs | 13800
11 | #REF! | 8400
12 | 4.4 Incentive system | 6180
13 | 5. Testing | 9600
14 | 6. Training, rollout, and support | 7020
Insert new rows above this one
|  | Cumulative EV | 14250 | 50350 | 98420 | 101840 | 105500 | 113255 | 118685 | 0 | 0 | 0 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period. | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012-2017 Vertex42 LLC
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1 | 4.3 Tracking system |  | Wk 1: 800; Wk 2: 250; Wk 3: 1500
2 | 2. Requirements definition |  | Wk 2: 900; Wk 3: 700; Wk 4: 1200; Wk 5: 1700
3 | 3. Web site design |  | Wk 3: 300; Wk 4: 300; Wk 5: 1250; Wk 6: 1500
6 | 3.3 Tracking system |  | Wk 3: 100; Wk 4: 500; Wk 5: 900; Wk 6: 700; Wk 7: 400
7 | 3.4 Incentive system |  | Wk 5: 400; Wk 6: 600; Wk 7: 500
8 | 4. Web site development
9 | 4.1 Registration for recreational programs
10 | 4.2 Registration for classes and programs
11 | #REF!
12 | 4.4 Incentive system
13 | 5. Testing
14 | 6. Training, rollout, and support
Insert new rows above this one
|  | Total Actual Cost | 800 | 1150 | 2600 | 2000 | 4250 | 2800 | 900 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 800 | 1950 | 4550 | 6550 | 10800 | 13600 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500

## ©
Earned Value Management (EVM) Template
By Vertex42.com
http://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2012-2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
http://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.